510 Sixteenth Street    Suite 100    Oakland CA 94612-1500    http://www.wid.org

Final Report 2009

Submitted to:

San Diego State University Research Foundation

Contract Number: #55655A P2699 7802

Submitted by:

Bryon R. MacDonald

Program Director

California Work Incentives Initiative - CWII

A Community Based Collaboration

World Institute on Disability

www.WID.org

510 16th Street, Suite 100

Oakland, CA 94612

Phone 510-251-4304

Cell 510-910-9726

Fax 510- 763-4109

TTY 510-208-9493

bryon@WID.org

Information Services

- Edit and update DB101 content for 2009 as appropriate to incorporate changes in federal, state and other rules/procedures for benefits programs.

- Refine DB101 website content and Benefits Planning Calculators based upon end user input and feedback from training participants and related evaluation survey instruments.

- Conduct DB101 website beta testing by end-users and subcontractors with programmatic expertise to improve on-line benefits planning session modules.

- Provide for web portal site technical maintenance and updates as needed, and when funds are not available through other sources.

- Distribute information to individuals via the “Employment Matters: News and Views from DB101” newsletter, containing news and information on current programs and practices supporting access to employment and healthcare for people with disabilities.

- Respond to DB101 forums and feedback forms, utilized by past-trainees and intended to support the ongoing learning process of these individuals.

- Produce professional versions of 5 Calculators: DB101 core team will adapt streamlined “professional” versions of calculator interfaces for California DB101, which are first being built for MN DB101. Professional versions could present all Calculator questions on a single long screen, giving rapid, one-glance access to the entire model.

- Produce PDF output for 5 Calculators: DB101 core team will create PDF summary versions of benefits planning sessions--as will be adapted from PDF output files being designed and built for MN DB101. This will give users access to summaries of session profiles and results in PDF format. Clients would then have a document to print for their own use, or to share with providers or others in-person or electronically.

Information services provided for the period of 1/1/2009-12/31/2009:

Editing and Updating:

During 2009, CWII staff edited or revised the following content sections for California DB101:

- Benefits Planners Directory (updated)

- CAPI

- DB101 Glossary (improved definitions)

- Life Situation: Sudden Onset

- Life Situation: Workforce Re-Entry

- Life Situation: Youth and Disability

- Medicare (expanded content)

- SSDI (including improved readability)

- SSI (general update and improvements)

- SSI calculations relevant to Calculators

- Text for the B2W Calculator

- Ticket To Work Program

This work included monitoring California program changes resulting from the budget crisis and updating DB101 content sections on an ongoing basis to address these changes. As an example, CWII completed all work needed to update SSI rates throughout the website and Calculators both for the May 1 and the July 1 SSI rate changes for numerous California SSI target groups.

CWII staff wrote and posted the following news articles on DB101:

CWII staff also wrote and posted the following news articles on DB101:

- SSI Recipients Can Now Report Wages by Telephone

- Social Security Must Provide Accessible Formats

- Americorps Program and Their Commitment to Inclusion

- The President and First Lady Seek Prospective Leaders for the White House Fellows Program

- Social Security Administration Makes Work a Reality with Individuals with Disabilities

Commissioner Astrue Asks Inspector General to Investigate California and Hawaii Disability Determination Services

- Eligibility Rules for Medicare Part D Low-Income Subsidy Change in 2010

http://www.disabilitybenefits101.org/news.htm

Refining and Testing:

The following refinements were made to the California DB101 Calculators and website during 2009. Some of these refinements were developed and designed as a result of usability and beta testing that took place in the State of Minnesota, and were then universally applied to all DB101 Calculators.

- Implemented event 'PASS goal achieved'

- Improved federal child tax credit to apply if child(ren) is under 17 at the end of the year

- Redesigned layout of Timeline in Calculator results sections

- Restyled, formatted, and resorted numerous Calculator Events for improved storytelling

- Re-organized and consolidated glossary categories

- Improved editing environment for Calculator Events

- Modified certain non-essential calculator Tips to prevent them from showing up on the list of tips at the end of the session.

- Trimmed all values from Benefits to Work Calculator’s Monthly Income/Expense Report that don’t occur in any plan or month. Dramatically improves readability.

- Purchased product upgrade and maintenance contract for easyPDF software component.

- Installed and activated new easyPDF component on development and production servers.

- Improved ability to hide various parts of the page layout when printing.

- New feature: Glossary popup window has a “Back” button when you click through to yet another glossary item.

- Applied COLA increases to IRWE/BWE

- Changed “Board and Care” choice to “Licensed Board and Care” to emphasize distinction.

Interface Fundamentals refinements/upgrades:

- Cascading Style Sheet makeover (support for XHTML 1.0 Transitional, improved treatment of sub-tables, heading font sizes, etc.)

- New page templates (reduce above-the-fold overhead, simplify layout)

- Start page redesign (simplified, improved organization, reduced graphics, Start button above fold)

- Session menu redesign (icons, text treatment)

- Banner redesign (DB101 + Calculator branding)

- Title bar makeover (title on white; remove calculator sub-brand)

- Progress bar

- “Saved session recording” notification feature

- New style sheet entries for new and modified interface elements

- Flowchart improvements (moved and reordered questions and tips)

These modifications can be seen in all DB101 California calculators: http://www.disabilitybenefits101.org/planning

Medi-Cal for the Working Disabled Calculator results refinements:

This deliverable includes a graphical treatment for the main messages, such as “You Qualify.” If the user qualifies for the 250% California Working Disabled program, the computed premium amount is integrated into the graphic. This can be seen in the new version of the Medi-Cal for the Working Disabled Calculator: http://www.disabilitybenefits101.org/planning/250_index.aspx

# B2W Results and Calculator Engine Elements:

# These deliverables include:

- Remove Income/Expense Spreadsheet

- Remove SSI detail

- Remove “Diving Deeper”

- Simplify results section menu (one line)

- Add Plan Toolbox (Make Changes, Create Another)

- “To-Do” column in Timeline

- Direct-to-month navigation in Monthly Income/Expense

- Fortune cookie organization/typography

- Support for “worse off” remedy feature

- Support for free Medi-Cal/250 simultaneity feature

- Remove many smaller fortune cookies

These modifications can be seen in the Benefits to Work California calculator:

http://www.disabilitybenefits101.org/planning/b2w2_index.aspx

With these deliverables, the California Benefits to Work Calculator has “caught up” to Minnesota’s. Infrastructure work done to support this effort will make it much easier to keep the calculators more parallel in the future.

Information Architecture:

Taken together, the Information Architecture deliverables comprise a thorough review of the organizational relationships among elements of the DB101-CA website.

As a result of the Information Architecture deliverables:

- All website elements will have a logical home

- Users will be able to find relevant content more quickly

- Users will find clear navigational pathways among related content elements

Home Page Redesign:

The design of the home page is the most prominent visual expression of the site’s information architecture.

The home page redesign addresses:

- Messaging. What is the best way to communicate the site’s main purpose and audiences?

- Nomenclature. How can we best describe the site’s components for rapid comprehension?

- Navigation. How best to dispatch users to the content and features of most use to them?

- Balance. How can we best make use of the home page’s limited real estate?

Detailed wireframe and design pre-visualization processes preceded implementation of the new home page.

Sitewide Navigation Redesign:

This deliverable addresses the functionality, look and feel of the sitewide navigation system (consisting of menus, hyperlinks and other elements) and its representations on the various pages of the site).

The Navigation System Redesign:

  - Expresses the site’s information architecture

  - Allows rapid navigation to frequently-used content

  - Is fully accessible to users of adaptive technologies

Grand Landing Pages:

Two levels of Grand Landing Pages collect related website sections and dispatch users among them. They are the manifestations of levels of information architecture below the home page but above the individual Content Sections. The redesigned site has Grand Landing pages for the following content divisions:

- Your Situation

- Work & Your Benefits

- Youth & Benefits

- New to Benefits

- Programs

  - Cash Benefits

  - Health Coverage

  - Career Planning

- Benefits Planning Calculators

## Individual Section Landing Pages:

Individual DB101 sections (Life Situations, Close-Ups, and Content Sections) include an array of pages focused on a particular topic. Section landing pages are the portals to that section’s content. The redesigned Section landing pages:

  - Briefly introduce the topic

  - Dispatch users to detailed content pages

  - Visually make clear the relative importance of the various content destinations (e.g., main article ahead of FAQs) while providing access to all parts.

## Resources Review:

The new “Also” boxes found on many pages of the site serve as a consistent and recognizable mechanism for “cross-linking” users from the section they’re currently in to related information elsewhere on DB101.

## Help Center Review:

The new “Talk to an Expert” box centralizes personalized user help in a prominent, consistent location on every page of the site. The box provides quick access to our statewide directory of trained Benefits Planners.

Employment Matters Newsletter:

During 2009, CWII produced and distributed four issues of Employment Matters: News and Views from Disability Benefits 101.

The first issue was distributed on February 26, 2009 to 493 subscribers. Topics included invitations to a CWG Public Policy Forum Teleconference and a Ticket to Work Employment Network California Teleconference, as well as the following articles:

- Resources for Individuals Who Are Homeless, Introducing new guidebooks and lecture series from Housing and Urban Development

- U.S. Labor Department To Begin New Monthly Data Series On People With Disabilities, Data will mark 1st official measure of unemployment rate facing Americans with disabilities

- Social Security Announces Nationwide Launch of Compassionate Allowances, This process will fast track applications for people with cancers and rare diseases

The second newsletter was distributed on June 30, 2009 to 527 subscribers. Topics included:

- Policy Update: AB 1269

More than surviving with Medi-Cal’s Working Disabled Program

- H.R 1205 ABLE Act of 2009

Achieving a Better Life Experience Act of 2009 or the ABLE Act of 2009

- SSA Access Ability: recruiting individuals with disabilities

SSA recruiting qualified applicants for career opportunities

- 2009 Ticket to Work Training Webinar Series: July 10, 2:00-3:00 pm ET

The third issue was distributed on September 10, 2009 to 1504 subscribers. Topics included:

- A save-the -ate reminder and information on the upcoming October 5 Town Hall Meeting, “Community Partners Respond to California Program Budget Cuts: Current Information and Strategies to Cope with Significant Change.”

- Eligibility Rules for Medicare Part D Low-Income Subsidy change in 2010: More people may qualify for “Extra Help” for Part D costs.

- A new automated wage reporting system is now in place in CA from SSA for SSI recipients (only) to report wages by telephone.

The fourth issue was distributed on December 14, 2009 to 1504 subscribers. It included the following articles:

- Commissioner Astrue Asks Inspector General to Investigate California and Hawaii Disability Determination Services;

- The President and First Lady Seeks Prospective Leaders for the White House Fellows Program;

- Social Security Administration Makes Work a Reality with Individuals with Disabilities;

- Americorps Program and Their Commitment to Inclusions;

- Social Security Administration must provide accessible format for people with visual impairments.

Responses to Forums and Feedback/Technical Assistance:

During 2009, CWII staff responded to 268 technical assistance questions received by phone, email and through DB101 Forums and Feedback. Technical assistance and support was provided to DB101 users and others on the following topics:

- Benefits Planning methods and strategies

- COBRA

- Employment Resources

- HIPP

- In Home Supportive Services

- Long Term Care

- Medi-Cal and Medi-Cal CA Working Disabled Program

- Medicare General

- Medicare Part D

- PASS

- Pell Grants

- SDI

- SSDI

- SSI

- Ticket to Work program

- TriCare

- Workers Compensation

- Working with Department of Rehabilitation

- Youth/Transition services and resources

In addition, Program Director Bryon MacDonald responded to 65 technical assistance requests via phone, email, and queries written into training exit evaluations from state Medi-Cal officials and eligibility workers; Department of Rehabilitation staff; One Stop Career Center; nonprofit service providers; and other training attendees. These technical assistance questions included requests for information on a variety of DB101 topic areas, new Ticket to Work regulations from 2008, 2009 IHSS and Medi-Cal budget cuts and program interaction issues with employment, Social Security rules and Medi-Cal’s California Working Disabled program, future information services, and upcoming events.

Professional Versions of Calculators and PDF Output:

WID contracted with Eightfold Way Consultants, our longtime partner in the development of DB101, to design and produce professional versions of 5 Calculators (streamlined “professional” versions of calculator interfaces) and PDF output for 5 Calculators (summaries of session profiles and results in PDF format).

Please see attached reports (Attachments I and II) for descriptions of these completed deliverables.

Technical Maintenance and Updates:

CWII staff and subcontractors performed the following technical maintenance of the DB101 website and Calculators in 2009:

- Fixed calculation bug in PASS Calculator

- Applied standard 3% indexing for COLA, wage growth, and inflation

- Fixed enumerated value quantity bug

- Suppressed 'FC SSI reduction'

- Set IRWE to zero when no earned income

- Updated SSP parameters for 7/1

- Fixed crashing none-type error.

- Fixed rent transition bug.

- Fixed "FC SSI-eligible" bug.

- Suppressed "FC ask for MSA" in the presence of "FC MSA-eligible" (redundant messaging).

- Corrected handling of SSI & MSA when being increased from zero in the first month.

- Suppressed recalculation of SSI/MSA eligibility when not SSA-disabled or SSA-blind.

- Disabled FC Disability Determination Needed. (See above. The calculator can no longer put someone on SS benefits who is not currently SSA-disability-determined.)

- Fixed crashing bug with a job quantity.

- Updated SSDI Work Rules illustration for 2009 figures

- Added parameter visualization facility for content editors

- Edited some calculator tips for 2009 figures

- Added glossary link visualization tool for content editors

- Fixed logic error in Benefits to Work Calculator that caused engine crash

- Fixed bug in glossary editor (items in multiple categories were displayed multiple times)

- Made MN glossary categories available in CA glossary editor, and vice versa

- Found and brought up to date numerous Spanish phrases in Calculators

- Migrated DB101 site traffic reporting from HitBox to Google Analytics

- Researched reporting mechanisms for both reporting tools

- Added item ID visualization feature for content editors

- Fixed two bugs in “search” editor feature: Glossary items and Events were being labeled as “orphaned text” instead of their true contexts being found.

- Resolved formatting issue in Spanish Youth and Work Calculator

- Deleted spam posts on Forums, deleted user and banned offending e-mail

- Fixed calculator bug: Work history quantities were not pre-populated with previous results when revisited.

- Fixed broken links to resources that have moved

- Uploaded new program parameters for Q2 2009

- Modified and updated page-creation automation system to support newer page types

- Tracked down locations where content could be universalized by using parameters, and made corresponding changes.

- Configured news article files.

- Data-entry for Spanish translations.

- Made it possible for parameters to have longer names.

- Imported new Part D parameters.

- Widened editor’s hyperlink popup dialog.

- Suppress glossary item context clues for all but editing site.

- Debugged technical problems associated with changing software component versions.

- Worked around Internet Explorer browser bug: width of username and password fields (when restoring Calculator session) were different by several pixels.

- Fixed font size problem on search result page

- Added search-again feature to search result page

- Fixed bug in calculator interface: Now quantities for children are properly prepopulated with old values when child pages are revisited.

- Fixed bug in glossary template: Now correctly lists multiple category contexts only for distinct items with the same title.

- Fixed bug in calculator interface: “Plan A” tabs now appear at proper elevation on Internet Explorer browser.

- Updated parameters for certain text formatting errors.

- Changed references to “Medigap” to “Medicare supplement.”

- Fixed page state bug involving saved sessions in Benefits to Work and School and Work Calculators.

- Add confirmation dialog when user clicks “Start Over” in an unsaved calculator session.

- Enhanced Calculator Events editor to allow viewing and editing smaller subsets of elements for enhanced performance.

- Perform user configuration maintenance on Groove.

- Changed generation of page templates to improve appearance on Internet Explorer

- Fixed appearance of Income/Expense Spreadsheet on Internet Explorer

- Fixed bug that hid a question (PASS in IRWE) on CA Benefits to Work Calculators

- Spanish data entry

- Published all versions of website on:

- Fixed small graphical glitch at bottom of Benefits to Work Calculator’s Monthly Income/Expense Report.

- Fixed bug leading to underlining of non-link content in Calculators when viewed in Internet Explorer.

- Renewed annual subscription for Spiderline site search software.

- Modified Calculator Event editor to display item sort order.

- Created parameters to refer to the synonymous programs CDB and DAC.

- Recategorized various glossary entries; fixed stray references to deleted glossary entries.

- Highlighted “Save Session” calculator button with icon

- Globally replaced link to SSDI application with new version

- Updated parameters for SSI/SSP rate declines

- New editor feature: When editing lists of items, show all categories to which each item belongs.

- Published all versions of website on:

- Rationalize Cascading Style Sheet font sizes in Forums application

- Reworked capitalization conventions for several terms of art: Extended Period of Eligibility, Trial Work month, Trial Work Period

- Fixed bug in Benefits to Work Calculator: Job transitions now show up properly in partial and full Timelines.

- Modified calculator beta report form to obfuscate e-mail address that was previously vulnerable to spam crawlers. Disabled spam-magnet address.

- Made COBRA continuation end date mandatory.

- Published all versions of website on:

- Managed effects of network outage at hosting provider.

- Restored Ticket to Work section to its old version, in preparation for new content entry.

- Fixed calculator bug: Deleting jobs led to incorrect choices for the default names of newly created jobs

- Fixed calculator bug: “Start Over” link was unreliable.

- Fixed calculator crash when restoring certain sessions.

- Updated typography and sort-order on various calculator “fortune cookies” for better storytelling.

- Traced cause of web editor crash. Fixed bad content and reported bug to vendor.

- Replaced dozens of references to automatic bookmarks (which are difficult to maintain) with manual bookmarks, throughout content sections.

- Set up web infrastructure and reconfigured menus for new CA Medicare section.

- Fixed bug in Pull Quote text filter.

- Update SSP figures for CA.

- Fixed formatting issues in Medicare section

- Globally fixed parameter spelling for Medicare Part B income limits

- Updated parameters for July, 2009

- Built and began to configure new content management server, using virtualization technology for enhanced maintainability.

- Adjusted additional parameters for July

- Fixed formatting issues in SSDI content section

- Repaired site-wide feedback form.

- Add wage subsidy information (when present) to calculator job summary line and PDF report.

- Globally replaced spelling of certain terms of art for consistency.

- Fixed content formatting issues.

- Added new parameter values.

- Fixed crashing bug in Forums.

- Documented workflow of form->mailgroup->mail recipients for various feedback mechanisms.

- Continued to configure new content management server.

- Updated server backup procedures.

- Purchased network storage for servers.

- Adjusted additional parameters for August.

- Tracked crashing bug in Benefits to Work Calculator.

- Fixed bug: Calculator error report form could itself crash if user pasted crash data from the Calculator into the form.

- Assisted in setup of private forums.

- Alphabetize display of Tips in tip editor.

- Uploaded and published “Getting Started Worksheet” for Benefits to Work Estimator.

- Instruct Forums administrators in mechanism for creating private forums.

- Fixed content management system bug involving physical size of dynamic images.

- Built advanced Content Management configuration tool allowing rapid comparison and reconciliation of similar pages across different sites.

- Rewrote code for results-section menus (all Calculators) for better maintainability.

- Continued to configure new content management server

- Responded to a Forums post about Forums user interface

- Fixed formatting bug in School and Work Calculator monthly income/expense page

- Fixed bug that inappropriately showed switch-scenario tabs in the Job to Job Calculator

- Consulted outside contractor on technical strategies

- Moved source code control database to new server

- Fixed bug: Saving a session immediately after creating a PDF report led the user back to a confusing XML document the user should never see.

- Fixed spacing bug: Calculator inline tips were too close to edges.

- Renewed annual subscription to Telerik user interface component software.

- Replaced “E-mail This Page to a Friend” form with a “mail to” link. Avoids spammer hijacking of this form.

- Fixed crashing bug in Work History screens of Benefits to Work Calculator

- Fixed text formatting issue in Work History screens

- Fixed incorrect counting of children (0-n instead of 1-n)

- Fixed text formatting on confirmation page: “Is this correct?” is bold

- Fixed old hyperlinks to content sections in Spanish quantities – should be glossary links

- Fixed calculator bug: “Previous” button on screen scen_create led to inappropriate screen.

- Extended Forums bad word list.

    - Renewed annual Spiderline software license (site search feature)

    - Added error-checking instrumentation around possible failure points in Benefits to Work Calculator interface code

    - Added javascript client code to ignore inappropriate multiple clicks on “Get This Session” buttons on saved session screen

    - Fixed certain glossary entries and categories

    - Remove references to obsolete “navigation toolbar” from Fortune Cookies

    - Fixed calculator bug (“Using the Title property of a Page…”)

    - Added backup hard drives for in-house servers

    - Created tool to ease management of multi-state versions of Calculator quantities, tips and events

    - Implemented “generic” quantity mechanism that makes maintenance of Calculator interface and engine much simpler

    - Managed core mailing list

    - Assisted with Forums login issues

    - Implemented generic tips mechanism; renamed and reorganized dozens of tips

    - Create “disconnected” version of Calculator interface. Works independently of engine; allows prototyping of interface flow before engine is implemented.

    - Fixed PDF Report bug in Calculators: PDF Report generation could fail when user clicks rapidly or repeatedly on the report preparation button.

    - Renewed DB101 domain names for 2 years

    - Improved offsite backup processes

    - Cleaned up About pages

    - Removed references to “modest” premium

    - Modified Calculator Editors to add awareness of “generic” quantities and tips

    - Modified Calculator Editors to support “cloning” of quantities and tips from another state

    - Alphabetized listings in Events editor to bring generic entries together with their state-specific equivalents

    - Added parameters to support the ability to refer to Medicaid buy-in programs and county social services agencies in state-independent content

    - Fixed formatting problems in Benefits at 18 Close-Up

    - Assisted with software setup and training of new employee

    - Renamed “Pro Interface” as “Power User Version”

    - Remove “Back”/“Next” buttons from Print Report page

    - Remove extra “Timeline” page title on Timeline page

    - Remove extra dark title on Session Summary page of Print Report

    - Maintained error report mailing lists

    - Added “Instant Edit” feature for quantities, events and tips – makes editing of these content items much quicker.

    - Accessibility feature: automatically label structural tables with ARIA role “presentation,” recognized by screen readers

    - Renewed software license and maintenance contract for web-editor software

    - Eliminated 5-year age limit on last Trial Work month in Benefits to Work

    - Fixed configuration error in Calculator redirection pages

    - Default Calculator variable to “Current Medicare without premium” if user is in both SSDI and SSI

    - Resort “SSDI decreases” event ahead of “SSI begins” (better explains causality in the timeline)

    - Implemented new and revised fortune cookies for Calculators

    - Updated and maintained Calculator program rules

    - Provided server hosting and maintenance

- Published all versions of website on:

  - 1/14/2009 (2009 figures)

  - 1/30/2009 (Calculator updates)

  - 2/4/2009 (Content changes)

  - 2/13/2009 (Content changes)

  - 2/18/2009 (To Do changes)

  - 2/23/2009 (Content changes)

  - 2/26/2009 (News articles)

  - 3/3/09 (News articles)

  - 3/13/09 (New content and features)

  - 3/16/09 (Fixed broken links - CA)

  - 3/17/09 (Bugfixes)

  - 3/25/09 (Many fixes)

  - 3/30/09 (News)

  - 4/13/09 (Benefits Planners)

  - 4/21/09 (New content)

  - 4/28/09 (Parameter changes)

  - 4/29/09 (New content)

  - 5/20/09 (News)

  - 5/26/09 (beta spam)

  - 6/8/2009 (New features)

  - 6/11/2009 (Bug fixes)

  - 6/15/2009 (Ticket to Work; Tip/Event edits)

  - 6/21/2009 (Ticket to Work edits)

  - 6/30/2009 (SSI/SSP updates)

    - 7/6/09 (Benefits Planner Directory)

    - 7/7/09 (Parameters and content edits)

    - 7/15/2009 (content edits; parameter updates)

    - 7/17/2009 (content edits)

    - 7/22/2009 (content edits)

    - 7/23/2009 (Forums fix)

    - 8/14/2009 (Medicare updates)

    - 8/17/2009 (Medicare updates)

- 9/14/2009 (New features)

- 9/15/2009 (Parameter fix)

- 9/16/2009 (PDF report/Save session bug fix)

- 9/23/2009 (Interface updates/Bug fixes)

- 9/28/2009 (News article)

  - 10/05/2009 (News article edits, glossary fixes)

  - 10/12/2009 (Calculator bugfix)

  - 10/19/2009 (ProVersion trials)

  - 10/20/2009 (ProVersion trials)

  - 10/21/2009 (ProVersion trials)

  - 11/1/2009 (SSI parameters)

  - 11/18/2009 (About pages)

  - 12/3/2009 (Benefits at 18 update)

  - 12/10/2009 (News articles)

  - 12/16/2009 (Calculator content)

  - 12/21/2009 (Calculators)

  - 12/22/2009 (Calculators)

  - 12/23/2009 (Calculators)

Online Services Comments from the Program Director:

In March of this 2009, the Minnesota MIG, in coordination with California MIG partners, conducted formal usability testing of DB101 online tools and information services. A significant amount of CWII staff time was devoted to the process of usability testing and to the follow-up activities and refinements resulting from the testing that are currently in production and beta testing phases for Minnesota.

The good news for California is that costs for this formal testing born by Minnesota have netted California DB101 refinements and improvements that increase overall ease of navigation of the website and online Calculators. This means a more user-friendly DB101environment that better enables website visitors to find the information and answers that they seek without getting “lost” in the vast world of benefits information. This prototype two-state coordinated testing effort shows promise to increase transparency for online services being sought in a multi-state environment--developments that can also mean higher rates of return for the investment of public dollars in the ever changing world of online technologies and benefits planning information services.

This year has been one of tremendous growth and learning for CWII on how to best design process and procedures that can produce even more cost-effective, high-quality services. Since, CWII has been engaged in ongoing learning about how to best manage and operationalize DB101 “version control” -- that is, how to best upgrade and improve online services in a multi-state environment within cost effective, non-repetitive, non-duplicative methodologies whenever possible. The progress we are making with multi-state process and procedures will ultimately lead to overall cost savings and enhanced product quality for states using DB101 Information Services, which will in turn increase the attractiveness of DB101 for other states interested in procuring these online services.  The development of multi-state processes and procedures can also lead to improved inter-state collaboration and cost sharing, as well as a better understanding (transparency) among states regarding the costs and fee structure associated with new services and maintenance of existing services.

TANF Calculator

- Enhance the existing California DB101 Benefits-to-Work Calculator to better serve CalWORKS families who have a family member with a disability (as described in Feasibility and Utility of Expanding Web-based Tools and Information for People with Disabilities who Access the CalWORKs Program and Utility of Expanding Web-based Tools and Information for People with Disabilities who Access the CalWORKs)

- Provide technical advice on the calculator to CHIIP and its research contractor for an intervention study with the Department of Social Services.

TANF Calculator services provided for the period of 1/1/2009-9/30/2009:

Because of state budget cuts resulting in significant changes to the CalWORKs program, WID and CHIIP mutually agreed to delay the development of a TANF/CalWORKS calculator until program changes can be thoroughly analyzed and the future of the program is more certain.

WID contracted with ECONorthwest to research and produce an updated report on recommendations for production of a TANF/CalWORKS calculator in light of results from the Minnesota-funded DB101 usability report, the current state budget crisis, and pending changes to the CalWORKS program. Since 2003, ECONorthwest is WID’s long term partner in the development of DB101 Calculators and has produced award winning benefits calculation products for several other entities which include TANF-related calculations, such as Los Angeles County Helps!

Please see Attachment III for updated recommendations and Attachment IV for the original CalWORKS report submitted to CHIIP in 2008.

WID has maintained ongoing communication with CHIIP regarding the status of the CalWORKS program and a potential intervention study with the Department of Social Services.

Veterans Calculator

- Coordinate, develop and produce a VA Benefits Online Tools Boundaries Outline Report for the development of a veterans-focused website with Veterans Online Benefits and Employment Tools and Information Services (as described in the Veterans’ Benefits Online Tools Findings Project, Final Report submitted in 2008 by World Institute on Disability and partners).

Veterans Calculator services provided for the period of 1/1/2009-12/31/2009:

Project Background:

In the fall of 2008, the World Institute on Disability facilitated six meetings with veterans and disability organizations to assess how U.S. veterans obtain benefits information, and how veterans learn about benefit programs as they plan for paid work. The information and recommendations that grew out of those meetings are discussed in the Veterans Benefits Online Tools Findings Report submitted to CHIIP in 2008. With universal consensus from the project’s subject matter experts, the Veterans’ Benefits Online Tools Findings Project Report specifically recommends the development of the following national online tools to help address the information deficits that disabled Veterans currently encounter when seeking support related to benefits and employment:

- An Online Veterans’ Benefits Information Navigator Tool. An informational guide to Veterans Administration (VA) and Department of Defense (DoD) veterans’ programs on a web-based portal featuring an interactive front-end “Navigator” tool that will lead the user quickly to appropriate programs for that user’s situation.

- A Veterans’ Benefits and Work Calculator. An online calculator that produces credible estimates of the effects of paid work on veterans’ and related benefits for Veterans who are receiving Disability Compensation or Disability Pension and considering paid work.

The Veterans’ Benefits Online Tools Findings Report also recommends that these online tools be embedded in a comprehensive informational website and housed and maintained by a non-profit organization outside of government.

Veterans Calculator Activities:

CWII prepared for and launched the Phase II formal meeting process during the second report period of the contract. WID enlisted Vietnam Veterans of America, Inc. and experts from Veterans of Modern Warfare, two highly respected veteran non-profit organizations, to take lead roles within the Veterans Benefits 101 Core Team (VB101) in shaping the Phase II Report. Formal VB101 Core Team meetings started August 28 and were held every two weeks with work assignments and action steps in-between for the panel members.

During early expert panel project meetings, participants agreed to collate needed data for the Boundaries Report into hierarchical, structured sections on 1) veterans health care, 2) income supports, 3) education and training, 4) employment and 5) housing programs. Program interactions and other dynamic features are addressed in the Report within this framework. To enable panel experts to work individually in between meetings and assemble the needed program data in a coherent framework, ECONorthwest contributed their organizational expertise by taking input from panel meetings and constructing an online user-friendly project Matrix which panel members filled in. The VB101 Questions Matrix can be viewed at: http://vb101matrix.econw.com/

VB101 Questions Matrix program categories include:

- Health

- Income Maintenance

- Education and Training

- Employment

- Housing

Each of these categories has associated with it scores of programs and benefits that are available to eligible U.S. veterans. The VB101 Questions Matrix allows panel members to populate the general program categories with relevant benefits programs. In addition, each program category lists criteria related to program eligibility. Panel members continued to add to and refine the information contained in the VB101 questions Matrix through November. The development and refinement of the Matrix represents a critical step toward creation of the benefits navigator (screening tool) and veterans benefits calculator to be produced in Phase III. The Matrix provides the framework for the information, criteria, and questions that the navigator and calculator will use to ascertain an individual veteran’s life situation and the resources and programs for which he/she is eligible.

During the final quarter of 2009, the Veterans’ Experts Panel and VB101 Core Team continued discussion of and research on 1)Veterans’ benefit program interactions, 2) the proposed design of the VB101 tools and website, and 3) the production of the Phase II Boundaries Report, including coordination of the writing, reviewing, and editing of the report. Panel members continued to work individually in between meetings on the VB101 Questions Matrix, adding data to refine benefits program information.

In December 2009, WID and its partners successfully completed Phase II of the project: production of the Online Tools and Information Services Boundaries Outline Report  (please see Attachment V). The Veterans’ Online Tool Project Phase II Boundaries Report contains an overview of the project, explanation of methodology used in Phase II, and an analysis of the proposed VB101 tools their scope, and the accompanying website. The completion of this report represents a critical design step required to begin production of these online tools in Phase III in 2010.

Project Sustainability:

CWII and CHIIP continue to coordinate on multiple efforts to solicit non-MIG funds to launch and fund the major design and production work that we plan to begin in 2010 under Phase III of the project. All stakeholders who have become associated with this project, including the California Employment Development Department’s Veterans Services, agree on the urgent need to have these online tools available to US veterans to support their return to civilian life and employment. WID’s outreach related to the project has been in support of these fundraising efforts.

Project Outreach:

During 2009, WID submitted the Findings Report of the Veterans’ Benefits Online Tools Project to several disability and veterans organizations outside the Experts’ Panel for their comments and input. WID has posted the Findings Report on the DB101 website (www.db101.org), on WID’s website (www.wid.org), and disseminated it to other public media. WID and Phase II project partners have presented on the Veterans’ Benefits Online Tools Project in California and Washington, D.C.

Presentations to date include to the national Vietnam Veterans of America Employment/ Microenterprise (Economic Opportunities) Committee, the Veterans Entrepreneurship Task Force (VET-Force), the National Council on Independent Living, California State Independent Living Council, Disabled Student Union senior management of California’s Community Colleges, and members of the California Governor’s Committee on Employment of People with Disabilities.

During December 2009, Mr. MacDonald reviewed the Findings Report with John Kregel, Ph.D. and senior staff of the National Training Center for Social Security WIPA grantees at Virginia Commonwealth University in Richmond, Virginia. The Veterans’ Experts Panel members from Vietnam Veterans of American and Veterans of Modern Warfare presented on the Veterans Online Tool Project in detail to Assistant Secretary Raymond Jefferson and his senior staff at the Veterans Employment and Training Services (VETS) program of the U.S. Department of Labor in Washington, D.C.

Also this fall, MacDonald presented on the project and fielded questions at:

- The Consortium for Citizens with Disabilities Task Force on Employment;

  - The National Council on Independent Living Subcommittee on Employment and Social Security; and,

  - The California State Library Veterans Workgroup: Employment, Education, and Training, of the California Research Bureau. Approximately 40 California legislative staff, veterans’ service organization staff, and California Employment Development Department Veterans Services staff participated in presentations and an intensive afternoon dialogue with a group of eight veterans transitioning to civilian life.

Training Services

- Develop a California Train the Trainer Club. CWII will convene a select group of subject matter experts who have excellent training skills. In its first year (2009), the Club will gather, collate and craft consensus guidelines for use in state-focused training services on employment planning, benefits planning and financial planning for Californians with a disability.

- Prepare curricula, co-market and deliver in-service DB101 training sessions for California Department of Rehabilitation staff on health, benefits, work and disability. Collect point of exit evaluation forms from training participants and submit to CHIIP for analysis.

- On a CHIIP request basis, prepare, market and deliver presentations in-person (or via webcast) at conferences and statewide meetings to benefits planners, consumers, family members, educators, and staff of government and non-governmental agencies to demonstrate DB101 on-line benefits planning sessions with calculator features or on public policy matters relevant to this contract.

- WID agrees to (1) continue collaboration with CHIIP to continuously improve evaluation approaches to training and services funded through CHIIP; (2) develop evaluation forms and other evaluation tools in collaboration with CHIIP staff for trainings and presentations funded through CHIIP; (3) collect evaluation forms for all trainings and presentations funded through CHIIP; and (4) transmit the data forms to CHIIP for analysis.  WID further agrees to obtain e-mail approval from the CHIIP project director for all evaluation forms used on CHIIP funded activities and can assume approval if there is no comment after two weeks.

- Share evaluation results with others as appropriate, including CWG participants and/or federal partners.

Training services provided for the period of 1/1/2009-12/31/2009:

California Train-the-Trainer Club (CTTC):

CTTC Background:

The CTTC fills a statewide need to create standardized guidelines to promote, expand and improve plain language information services on disability benefits, employment, and asset accumulation--topical areas widely recognized as inaccessible due to 1) their complexity and 2) changing and evolving nature relative to their state and federal requirements, interactions and rule changes. For example, the ABLE Act of 2009, now pending in Congress, would significantly change how SSI recipients could plan, save, and receive training, education and health care services as they move towards taking on new employment. To effectively and accurately communicate important information and updates on work and benefits to people with disabilities throughout California, we need a consistent training approach that draws on the best practices of the experts statewide and incorporates plain-language training techniques that ensure the information imparted is understandable and accessible.

The CTTC approaches this challenge by bringing together a group of professionals who are seasoned experts on both the subject matter and producing training events. CWII asked a core group of benefits experts from government and non-profit organizations to join a series of teleconferences to this end and to help shape and define the CTTC. These individuals have the knowledge and experience to shape such a set of guidelines.

The CTTC has worked toward accomplishing its goals by:

- Crafting and collating a set of training guidelines that ultimately will provide consumers and professionals throughout the state with information that is uniformly current, correct and consistently delivered;

- Enlisting a cadre of California benefits planning trainers willing to apply these guidelines to California training activities focused on employment planning, benefits planning and financial planning.

CTTC members: The California Train-the-Trainer Club (CTTC): currently consists of the following members:

- Bryon MacDonald, CWII Program Director, WID, Oakland

- Mason O’Neal, CWII Program Analyst/Trainer, WID, Oakland

- Karla Bell, Benefits Expert, CHIIP, San Diego

- Michael J. Van Essen, Benefits Establishment Specialist, Pacific Clinics, Los Angeles

- Abygail C. Medina, MS, CRC, Manager, Social Security Programs Section, DOR
Ignacio Chavez, Community Work Incentives Coordinator (CWIC), DRAIL, Modesto

- Donna Reed, Community Work Incentives Coordinator (CWIC), CID Belmont, San Jose

- Randy Boyle, Senior Staff Attorney, National Health Law Program, NHeLP, Los Angeles

- Rachel Stewart, Program Manager, CHIIP, Sacramento

- Jacques Chambers, Benefits Counselor, private practice

- Christina Walters, Program Specialist, Operations & Procedures Team, Center for Disability, Social Security Administration Region IX

- John Riley, Community Work Incentives Coordinator (CWIC), AIDS Project Los Angeles, APLA

- Alana Theriualt, Benefits Counselor, AbiliCorp Employment Services, Oakland

- David Mon, Community Work Incentives Coordinator (CWIC), CID Belmont, San Mateo

- Teddie Joy Remhild, Consultant, CHIIP

- Megan Hellam, Program Analyst/Social Security Specialist, Social Security Programs Section, DOR

Email Addresses: kbell@interwork.sdsu.edu; Ignacio@drail.org; DonnaR@cidsanmateo.org; mason@wid.org; boyle@healthlaw.org; jacques@helpwithbenefits.com; jriley@apla.org; Davidm@cidsanmateo.org; Rachel.Stewart@dhcs.ca.gov; Christina.Walters@ssa.gov; alana.theriault@abilicorp.com, teddiejoy@att.net, MHellam@dor.ca.gov, ACMedina@dor.ca.gov

The CTTC Outreach Circle (interested stakeholders whom CWII keeps informed on project progress):

- Tom Foley, Access to Assets Project Manager, Acting Interim Executive Director, WID

- David Lipschutz, Senior Attorney, California Health Advocates, Los Angeles

- Catherine Campisi, CHIIP Consultant

- Cathy Senderling-McDonald, Program Analyst, County Welfare Directors Association, CWDA, Sacramento

- Janice Emerzian, Disabled Students Union Director

- Karen Davidson, Program Manager, Ticket to Success, Tulare County

Email Addresses: tom@wid.org; dlipschutz@cahealthadvocates.org; CCampisi@cccco.edu; csend@cwda.org; emerzian@scccd.org; kdavidson@see.tcoe.org

CTTC Project Activities:

During 2009, CWII prepared for and hosted 7 CTTC telephone meetings: two CTTC introductory project launch teleconferences on July 23 and July 30, followed by monthly meetings on August 20; September 17; October 15; November 19; and December 17.

During the two introductory calls, a ready consensus emerged on the need to develop statewide guidelines for trainers and online information services (integration) on the topical areas of employment planning, benefits planning, and financial planning--activities that Californians with a disability engage in. The group agreed to remain volunteer–based and to seek to recruit experts from diverse backgrounds. The CTTC has focused on two immediate objectives:

1) Help shape a series of consensus trainer and online information services guidelines;

2) Address and shape strategies in 2010 to offer the CTTC developed guidelines for use to a wide range of service providers and experts who produce and conduct training and presentation events and who use online services when providing employment related services.

At the meetings, CTTC members have shared resources and sample training curricula that they gathered, as well as sharing benefits news and information. Members worked together to produce the most recent draft of its Guidelines and Promising Practices for trainers to use in conducting benefits training events (please see Attachment VI). These guidelines offer best practices for how to present material and how to explain new terms, using multiple teaching styles, formats, etc. The Guidelines also contain suggestions for handout materials and Power Point presentations. The document captures the insights and skills of experienced trainers on public benefits.

In keeping with the CTTC’s objective of promoting statewide collaboration among experts, Randy Boyle, a senior attorney at NHeLP (National Health Law Program) and an active CTTC participant, introduced the early work of the CTTC to the Benchmark Institute, a respected statewide benefits training center in San Francisco. During the final quarter, the Benchmark Institute provided a webinar to CTTC members on training methods and techniques. The two groups are in discussion about potential joint training efforts.

The CTTC was successful in expanding its membership during this year. New CTTC members include: Abygail C. Medina, Manager, California Department of Rehabilitation; Teddie Joy Remhild, Consultant, California Health Incentives Improvement Project (CHIIP); Megan Hellam, Program Analyst/Social Security Specialist for the  California Department of Rehabilitation.

The group also began planning activities for 2010, including a CTTC retreat scheduled for the first quarter of the coming year.

California Department of Rehabilitation Trainings:

WID conducted six trainings for California Department of Rehabilitation staff. WID coordinated with DOR staff to schedule and conduct outreach for the trainings. WID staff also prepared curricula, training materials, and handouts for the trainings focusing on health, benefits, work and disability. All Training Exit Evaluation forms have been forwarded to CHIIP for analysis.

DOR trainings took place on the following dates:

- February 19, 2009: DB101 in-service training for DOR staff in Ontario, CA.

23 participants from DOR and SSA. The following are excerpts from post training evaluations:

- "I have been fortunate enough to go to this training before. The information is still useful and trainer is great!" aspivey@dor.gov

- "Every time I've attended a "benefits training" there are contradictions in the info provided. I feel most confident with your presentation."

- February 24, 2009: DB101 in-service training for DOR staff in Sacramento, CA.

22 participants from DOR. The following are excerpts from post training evaluations:

  - "Should be mandatory to ALL DOR employees."

  - "Train trainers in staff development to train pieces of this for people working with different disability groups (teens, youth blind & visually impaired, deaf & hearing impaired, etc.) this should be required for all RCS. People should be able to repeat it for additional CRC hours because there is so much to learn. You can call it DB101-A, DB101-B, etc. so CRC will accept it."

- "Bryon was a fabulous presenter. Intelligent, intuitive, and empathetic. Humorous too. I appreciate that he admits when he doesn't know an answer. It was great having Ed here too." (Ed Wrona is one of SSA’s CA Area Work Incentives Coordinators, and one of the regular DB101 training event technical assistants provided pro bono by SSA Region IX.)

- March 18, 2009: DB101 in-service for DOR staff in Costa Mesa, CA.

21 participants from DOR. The following are excerpts from post training evaluations:

What about the training was most helpful to you? (Exit Evaluation Question):

- “Use of calculator with instructor's sharing”

- “The calculator program”

- “Everything. Training needs to be provided to all DOR staff and could be extended to   implement specialists (vendors)”

- “The information was presented in an excellent visual format”

- April 9, 2009: DB101 in-service training for DOR staff in Oakland, CA.

13 participants from DOR, Korean Community Center of the East Bay, SSA Regional Office, World Impact. The following are excerpts from post training evaluations:

- "I would still send my clients to Social Security but with better instructions for questions to ask and record keeping."

- "I would attend this training again for a refresher!"

- “This is the kind of material that would be helpful to use frequently or I would tend to lose it. I now know how much I don’t know!

- September 23, 2009: DB101 in-service training for DOR staff in Los Angeles, California

36 participants from DOR.

- “DOR should have this training 1x a year because of all the changes every year.”

- “I would like this offered at least 1x a year. The more I hear it, the better I understand the material and become a competent resource to my clients.”

- “Big picture perspective and great interaction encouraged.”

- December 2, 2009: DB101 in-service training for DOR staff in Concord, California.

33 participants from DOR. All training attendees reported that their knowledge of specific disability-related benefits improved or greatly improved as a result of the trainings. The great majority of attendees reported that after the training, they were more confident that people with disabilities can pursue work and access the information and resources needed on employment and benefits. The training participants were very interested in the material and asked questions throughout the day of training.  At their request, participants received training on how to conduct research on benefits rules, and important websites and organizations they can use when making referrals.

Other Presentations and Outreach :

In addition to the DOR trainings described above, WID conducted trainings on disability benefits, employment, and the DB101 website. Training activities included:

- Scheduling trainings with multiple community groups and organizations.

- Coordinating travel planning and logistics for trainers.

- Coordinating site logistics, registration, and outreach

- Preparation and reproduction of curricula, materials and handouts

- Conducting trainings on disability benefits and employment

- Administering and obtaining exit evaluation information to share with CHIIP.

WID conducted the following trainings during 2009:

January 14, 2009: New Tools for Success Training.

  - Hosted by East Bay Innovations

  - Location: Village High School, Pleasanton, CA

  - Participants: 20 parents and family members of people with disabilities.

March 10, 2009: Ticket to Work Program.

  - Hosted by Department of Labor, Employment and Training Administration

  - Location: Teleconference.

  - Participants: State-level representatives from the DPN projects, and representatives associated with the DOL National and Regional (Federal Project Officers) offices, Social Security Administration, and the NDI TA Team (the national Technical Assistance provider).

May 14, 2009: Veterans Online Tools Project Presentation.

  - Hosted by California Disabled Students Unions.

  - Location: Riverside Community College, Riverside, CA.

  - Participants: 100 people with disabilities and representatives from Disabled Student Unions.

June 4, 2009: Veterans Online Tools Project Presentation.

  - Hosted by California Governor’s Committee on Employment of People with Disabilities.

  - Location: San Diego, CA.

  - Participants: 50.

June 5, 2009: MIG partnerships and Veterans Online Tool Project.

  - Co-presentation with Access to Assets and the Arizona Bridge to Independent Living.

  - Hosted by National Council on Independent Living (NCIL)

  - Location: Washington, D.C.

  - Participants: 50 representatives from NCIL and MIG grantees.

July 28: Youth Leadership Forum Resources Fair. CWII Projects Coordinator Sylvia Kim demonstrated DB101 online tools at the Youth Leadership Forum Resources Fair and distributed a youth survey asking youth for input on what they need from the Internet regarding employment and benefits planning information services.

August 26: California Health Advocates (CHA) monthly California Medicare Coalition. Program Director Bryon MacDonald was the invited guest speakerat CHA’s monthly California Medicare Coalition teleconference. Mr. MacDonald presented on Medi-Cal’s California Working Disabled Program and reviewed improvements to the program contained in AB 1269, as well as providing other federal updates on SSA work incentives. CHA trains HICAP volunteers and otherwise serves the information needs of Medicare beneficiaries of all ages in California.

October 5: Town Hall Meeting on Budget Crisis. On October 5, 2009, WID hosted a statewide conference to provide information and education on the impact of pending state budget cuts for people with disabilities. The meeting took place simultaneously at three locations (Los Angeles, Oakland and Bakersfield) using tele-video conference technology provided by The California Endowment. The State Council on Development Disabilities provided support for guest speaker honoraria. The town hall conference featured top subject matter experts on Medi-Cal, IHSS, and other programs as guest speakers. The presenters provided information in a plain language format on the anticipated impact of state budget cuts, including updates from Assistant Secretary Megan Juring for Long Term Care Services, CA Health and Human Services

October 8, 2009: 23rd Annual Supported Conference (Sacramento, CA).

Bryon MacDonald co-presented with keynote speaker Molly Sullivan of Griffin Hammis Associates on work incentives and Plans to Achieve Self Support (PASS) at the 23rd annual Supported Life conference hosted by the Supported Life Institute and Area Board 3. MacDonald demonstrated a full Benefits to Work DB101 Calculator scenario/demonstration via Internet to an audience of 35 parents, family members and adults with a developmental disability.

Evaluation:

Howard Twomey of SDSU Interwork Institute and CWII have worked together to develop exit surveys that help measure usability and usefulness of online tools. DB101 users can access these surveys when they complete a DB101 calculator session (on the final page).

WID uses the Post Training Exit Evaluation form developed in collaboration with SDSU Interwork Institute at all our trainings. Copies of all these evaluation forms are shared directly with Interwork Institute.

Public Policy Development

- Consultant services supporting CHIIP goals consistent with those of the California Comprehensive Strategy for the Employment of People with Disabilities of (1) conducting research and/or policy analysis supporting improvements in health incentives and other supports for people with disabilities, and (2) ensuring sustainability of systemic employment supports beyond the life of the grant with activities to include:

  - Maintain a vehicle for stakeholder input on policy improvements needed to increase the employment, access to healthcare and self-sufficiency for Californians with disabilities through the California Work Group on Work Incentives and Health Care (including at least 4 statewide conference calls);

  - Gather consensus recommendations with CWG participants that could improve state systems or partnerships which support employment and access to health coverage for Californians with a disability;

  - Directly advise & consult on implementation of public policy matters that serve to implement the California Comprehensive Strategy for the Employment of People with Disabilities, particularly related to Medi-Cal’s California Working Disabled Program, In-Home Supportive Services and access to workplace personal assistance; and,

  - Educate policymakers (in the legislative & executive branches of government) about the California Comprehensive Strategy for the Employment of People with Disabilities, particularly related to Medi-Cal’s California Working Disabled program, In-Home Supportive Services and access to workplace personal assistance.

Public policy services provided for the period of 1/1/2009-12/31/2009:

The Historic Passage of AB 1269:

On October 11, 2009, Governor Schwarzenegger signed AB 1269 into law—a great accomplishment for the disability community in a year in which so many benefits programs in California were drastically cut or eliminated. AB 1269 makes needed improvements to Medi-Cal’s California Working Disabled Program by allowing disabled workers to be able to save their earnings with no cap on the savings so as to better plan for the future. With the law fully implemented, those enrolled in the program will have 26 weeks in-between jobs during which they can stay on Medi-Cal through this program without penalty—an especially important provision in light of current unemployment rates and economic challenges. In addition, AB 1269 allows enrollees of all ages to stay in the program and continue working by exempting Social Security disability insurance income that has converted to Social Security retirement income. The new law makes modest, affordable changes to the monthly premium structure so that enrollees contribute to the increasing costs of US health coverage, the first premium structure increases since the program’s start in April of 2000.

As the bill’s sponsor, WID provided technical assistance and expert advice to the bill’s author, Assemblywoman Julia Brownley (Santa Monica); other legislative staff; and state agency health services staff. WID also provided education and outreach on the bill through the California Work Group (CWG).

AB 287 (Beall):

AB 287 (Beall) also became law in 2009 mandating that California develop an Employment First policy in 2010 for Californians with a developmental disability. AB 287 is an outgrowth of public policy initiatives initiated by SB 1270 (Chesbro) calling for increased employment support programs for California Regional Center clients and others with a developmental disability in California. WID provided technical assistance and public education activities on AB 287 during the report period.

CHIIP:  MIG Infrastructure Sustainability:

During the report period, WID staff began a series of focused discussions with CHIIP and Governor’s Committee members and staff on sustainability of the infrastructure that the California MIG (CHIIP) has contributed significant support to building since 2003. A series of meetings in early 2010 are planned as a result of these discussions between WID, the San Diego State University Interwork Institute, and the Governor’s Committee Policy and Planning Committee on implementing more of the California Comprehensive Strategy on Employment of People with Disabilities at a faster pace, in direct conjunction with identifying the long-term statewide funding strategies needed to support and sustain such activity.

In this context, WID will publish in January 2010, Streamlining and Coordinating Employment Services and Benefits Planning to Meet the Challenges of Hard Economic Times, Public Policy Recommendations on the National Economic Imperative to Improve Employment Outcomes of People with Disabilities. The public policy report is a collaboration of the Stanislaus County and the Santa Clara County Work Incentives Groups with technical assistance and support from The California Health Incentives Improvement Project at the Interwork Institute, San Diego State University. WID expects to present on the reports’ extensive recommendations to the Governor’s Committee in early 2010 as one methodology to keep a laser focus on improving the systems that support employment outcomes.

California Work Group on Work Incentives and Health Care (CWG) meetings:

CWII provides ongoing support for the CWG, including regular email correspondence and updates, scheduling meetings, maintenance and updating of the membership database, teleconference services, and administrative and clerical support, such as taking minutes and responding to CWG member questions and comments. Over the course of the contract, WID staff drafted and broadcast 26 informational emails to between 1,463 and 1,652 active CWG members. Email communications included updates on the status of AB 1269; information on the CWG Policy Meeting series and other upcoming meetings; and information on the impact of the California budget cuts.

During 2009, CWII hosted and facilitated the following CWG statewide teleconferences, including the 2009 CWG Summer and Fall Policy Meeting series:

April 10, 2009. The Honorable Tony Sauer, Director of the California Department of Rehabilitation, participated as the CWG guest speaker. Mr. Sauer provided inspiring personal and professional perspectives on the meeting topic: “California Employment during Hard Times.” Close to forty CWG participants joined the call and participated in the group discussion following his presentation.

June 26, 2009. Guest Speakers Marty Omoto of CDCAN and Karen Keeslar, a highly regarded Sacramento-based disability expert, presented in plain language overviews on the California Budget Crisis to date. The speakers provided accurate, up-to-date news on the budget crisis and its likely impact to those who use Medi-Cal, IHSS, SSI and other community and employment supports. A CWG record breaking 76 individuals and group representatives participated in teleconference and difficult discussions that followed.

August 21, 2009. Guest speakers included the Honorable Mariko Yamada and California Expert Policy Analyst Cathy Senderling-McDonald from the California Welfare Directors Association (CWDA). The Topic was "Innovation and Renewed Creativity in Local and County Government Social Services Networks: Employment Supports in Hard Economic Times for California." WID facilitated a dynamic discussion among participants on budget cuts and what they mean to IHSS recipients, as well as the optional benefit cuts under the Medi-Cal program. There were 40 participants.

October 27, 2009. Employment and Work Incentive Updates for California Workers and Job Seekers with a Disability. The teleconference included updates on: One Stop Career Centers and Plans for 2010; The Governor’s Committee on Employment of People with Disabilities and Plans for 2010; and details on what the Governor signed into law with AB 1269 on October 11, 2009. Guest speakers included Dennis Petrie, Deputy Director of Workforce Services for the California Employment Development Department and Paul Miller, Chair of California Governor's Committee on Employment of People with Disabilities. Ninety eight CWG members participated in the call and question and answer session after the guest speakers.

November 12, 2009. Youth and Transition: Synchronizing Youth Career Planning and Information Services. Guest speakers for this teleconference included: Rebecca Cokley, Confidential Assistant at the U.S. Department of Education, Office of Special Education and Rehabilitative Services; Rachel Stewart, Program Manager for the California Health Incentives Improvement Project (CHIIP); and Catherine Campisi, former Director of the California Department of Rehabilitation and Faculty Consultant for California Health Incentives Improvement Project (CHIIP). Fifty CWG members participated in the teleconference. An in depth range of information was presented by the speakers including overviews of the Youth in Transition TOOLKIT under development by CHIIP staff. Rebecca Cokley from Washington referenced that a good deal of discussion is underway with the new Administration to establish a National Commission on People with Disabilities, Employment, Economic Empowerment and Social Security.

November 19, 2009. IHSS and Medi-Cal State Budget Cuts Implementation Updates. This teleconference featured guest speakers 1) Karen Keeslar, a public policy consultant with Keesler & Associates Government Relations and 2) Cathy Senderling McDonald, senior legislative advocate with the California Welfare Directors Association. The teleconference was attended by 30 CWG members, including service providers, people with disabilities and government agency representatives.

Other public policy activities:

On July 7, 2009, Bryon MacDonald participated in the Governor’s Committee Policy and Planning Subcommittee meeting.

On July 21, 2009, WID sponsored  a two-county Work Incentives Group Policy and Planning Retreat. WID incorporated benefits counselor findings from the CHIIP two-day statewide Benefits Planning Summit December 2008 into this all day discussion framing topical issues and recommendations for a policy report to be published later this year, draft title Two County Policy Report on Benefits Planning in Hard Times. CHIIP Project Director Eric Glunt, Program Analyst Rachel Stewart and CHIIP consultant benefits expert Michael Van Essen from Los Angeles participated.

On July 22, 2009, Bryon MacDonald met with Chairs of the National Council on Independent Living’s Health Care and Long Term Care Committees to discuss relevance of employment status and Medicaid-Buy-Ins inside the national Health Care Reform (HCR) proposals in Congress. While consensus that employment status being eliminated as a barrier to health care, little hope is warranted at this stage that HCR reform will be inclusive of Medicaid Buy-In issues or expansion, in the first year of reform anyway.

On July 31, 2009, Bryon MacDonald participated in a DOR-Ticket to Work (TTW) Pilot Program concept and brainstorming call. Participants included Abby Medina, Tom Heinz, Linda Ratner (EBI) and Lynn Rivas CDSNN. A DOR-EN Pilot program for East Bay and San Jose DOR Districts is in internal design stages to enable more Supported Employment (SE) providers to secure Phase I payments in the Ticket to Work Program when DOR closes a case with the client earning very low monthly wages. The PILOT designs and parameters are being vetted with senior DOR staff and discussed at SSA in Baltimore. Mr. MacDonald has offered ongoing TTW technical assistance (TA) to all parties via phone, email and phone meetings on the need and realistic way the pilot could be set up and run.

On August 3, 2009, with technical assistance from CHIIP staff, CWII revised and updated a cost and revenue analysis in the event that AB 1269 is enacted into law: AB 1269 (Brownley) Could Increase State Revenue and Offset Medi-Cal Costs (After the enactment and implementation dates for legislative provisions and CMS approval of a CA Medicaid State Plan Amendment), 2009, World Institute on Disability. The short, thorough analysis was sent to many California health care services departments and became widely read in August and September by key government analysts studying the policy initiative. Mr. MacDonald fielded several phone calls from government stakeholders providing further background on the cost analysis and WID experience with Medi-Cal recipients who use private health care coverage as the primary payer alongside eligibility for Medi-Cal services. Please see Attachment: AB 1269-state revenue-costs.

On August 13, 2009, Bryon MacDonald presented to the Olmstead Advisory Committee (OAC) meeting on Medi-Cal’s California Working Disabled Program (CWD) and the then-pending AB 1269 (Brownley) improvements to that program; co-presented with Eric Glunt of CHIIP who provided an update and overview on CHIIP activities related to California’s Medicaid Buy-In and other initiatives.

On August 24, 2009, WID (AB 1269 sponsor) met with Health and Human Services Agency Secretary Kim Belshe' and Author Assembly Member Julia Brownley, and their senior staff at the author's offices in the Capitol.  All technical discussions needed on current bill language were vetted to the satisfaction of all participating. CA HHSA and the Secretary were eager to have this policy initiative enacted into law.

On September 14, 2009, at Mr. MacDonald’s request, Dan O’Brien, Acting Associate Commissioner for the OESP, and Mr. MacDonald discussed new complex rules to be found in the new RFP for employment networks to apply to be service providers in the Ticket to Work Program. The call was substantive and productive, resulting in follow-up calls and emails and improved procedural changes on how ENs need to report to SSA when requesting certain TTW milestone payments.

On October, 29, 2009, Bryon MacDonald participated in a national Employment Taskforce teleconference meeting of the Consortium for Citizens with Disabilities (CCD). The purpose of the meeting was to discuss and provide input on concepts and provisions to be included in a potential national employment bill. The meeting was held in response to Senator Harkin’s expressed interest in sponsoring such legislation. Mr. MacDonald presented on and outlined the key policy concepts articulated and discussed in a series of written discussion topics collated into the policy brief: Being American: the Way Out of Poverty (WID 2006).

On November 5, 2009, Mr. MacDonald participated as a member in the all day HHSA Olmstead Advisory Committee Meeting in Sacramento. He presented prepared public comments and data on why the DHCS Concept Paper and plans to draft a Section 1115 waiver should include provisions for improving the plight of the underinsured in California as well as the current concept of focusing only on the uninsured. He articulated public remarks that a continued narrow focus on only discreet and high cost health services populations serves to build and strengthen bureaucratic silos in the health care industry for only the significantly ill or disabled, further weakening their real opportunity over time to access health services, as they have no political clout compared with the industry itself.  He also articulated public inquiries to an HHSA guest speaker from Washington on the federal status of the CLASS Act and the Community Choices Option in federal pending health care reform legislation.

On November 9, 2009, Mr. MacDonald conferred for an hour via phone with Department of Rehabilitation Director Anthony Sauer on the status and progress of the Veterans’ Online Tools Project and the two County work incentives public policy report to policy makers and program administrators. Mr. Sauer expressed his appreciation for the updates and for receiving information that his staff has been engaged in contributing input to both WID projects.

On November 16, 2009, Mr. MacDonald prepared for and participated in a two-hour meeting via phone as member of the Policy and Planning Subcommittee of the CA Governor’s Committee on Employment of People with Disabilities. Topical issues discussed included AB 1269 becoming law in October, other Comprehensive Strategy successes in 2009, and planning for policy and sustainability strategies for Comprehensive Strategy activites and initiatives for 2010 and 2011. There was wide consensus in the meeting that the state budget crisis will affect people with disabilities in California negatively for several years to come, and that enhancing any employment and return to work outcomes for this population was priority activity considering the recession and state crisis. The California Working Disabled Program (CWD) was discussed as an even more important work incentive and tool in this context.

On November 18, 2009, Bryon MacDonald, a NASI Member, was an invited Moderator in a National Academy of Social Insurance (NASI) public policy and research seminar (co-sponsored by the Social Security Administration and the National Academy of Social Insurance) to promote dialogue and understanding among experts from the nation’s two largest disability income maintenance programs: Social Security Disability Insurance (SSDI) and Workers’ Compensation. Bryon MacDonald served as the Moderator on the Innovations in Return to Work panel. Seminar participants included researchers, senior state and federal government administrators, labor representatives, advocates, and community based organizations involved with studying, managing and improving SSDI and the return to work initiatives and efforts in Worker’s Compensation.

During the final report period, MacDonald was invited and joined the Justice for All Action Network Employment Team, a national group of organizations that are, like WID, run by people with disabilities and focused on full participation and economic well-being. He became a key writer and contributor for a draft Executive Order to create a national Commission on People with Disabilities, Employment, Economic Well Being and Social Security, to launch in 2010 coinciding with the 20th Anniversary of the Americans with Disabilies Act (ADA). The draft proposal has been approved by a wide variety of disability organizations outside government and formally submitted to the Obama Administration just before Christmas for their review and consideration.

Consultation on Implementation of Public Policy Matters:

During 2009, a California Department of Rehabilitation pilot program has been in the discussion and draft stages to better enhance the Partnership Plus Program in the newly revised Social Security Ticket to Work Program.  In brief, when the California Department of Rehabilitation (DOR) helps a consumer find paid work and then closes the case (Case 26 Closure) and the wages being earned are very low (under $700/month) there is no allowance for an Employment Network in the Ticket to Work Program to help the wage earner earn more money and so gain access to the EN Phase I Milestone Payments in the new Ticket Program. Currently, when DOR closes the case for low wage earners in these situations, no one can capture the almost $5,000 Ticket Program Phase I Milestone payments per Social Security’s new rules.

CWII Program Director Bryon MacDonald, policy consultant Dion Aroner, and the principals at East Bay Innovations (supported employment vendors) and the Consumer Directed Services Network (CDSN) met regularly via phone and have also met with DOR senior staff, including one in-person meeting with DOR Director Tony Sauer, Deputy Director Lana Fraser, and other senior DOR management. Mr. MacDonald met privately with DOR staff on multiple occasions on these topics during the report period. WID and DOR have collected relevant data as part of these discussions that indicate a significant pool of consumers could benefit from the pilot program under review and discussion. There is a mutual support and interest in crafting a California pilot program within current law and regulations to be able to serve more consumers in supported employment and help them attain higher wages in these situations. As of the date of the writing of this report, there are confirmed plans for a meeting with representatives from the Department of Rehabilitation, SSA Office of Employment Support Programs, and CWII in mid February 2010 during the Department of Labor’s Listening Session in the Bay Area (part of a series of six Listening Sessions across the country to provide an opportunity for members of the public to provide input to senior federal officials on their ideas for more effective ways to employ women, Veterans and minorities with disabilities, and what is currently working in their communities to increase employment among people with disabilities).